## ورقة1
# | Template Features | Time / Days | Status | Comments
1 | Template design | 1 | Done | Selection from available templates to match the basic requirements
2 | Project Architecture | 3 | Done | Identify the best practice to implement levels
3 | Environment preparation | 3 | Done | Install .net 8 framework and last visual studio updates
4 | project source file |  | Done
5 | Project levels creation |  | Done
6 | New Github repository |  | Done | https://github.com/mussab87/Template_V2New
7 | Code sync and pushing |  | Done
8 | Add design to the project | 3 | Done | Adding design files and pages into the project and displaying and asure everything linked and working
9 | Database entities creation | 10 | Done | Prepare database context file | Framework | Version | Type | End of Support
10 | Custom identity tables |  | Done | Identity, User, Role, Role permissions models classes | .Net 8 | 8.0.14 | Long Term Support | 2026-10-11
11 | Database migration |  | Done
12 | Seek default values |  | Done | Admin user, Roles, Role Permissions
13 | Authentication and Authorization |  | Done | Install required packages and libraries
14 | Startup setup |  | Done | Add required services and configurations into program files
15 | Login page | 3 | Done | Design, validation
16 | Captcha |  | Done | Adding verification picture on login page contains random numbers
17 | Login process | 2 | Done
18 | Landing page |  | Done
19 | Admin Control pages | 10 | Done | user, role, role permissions management
20 | Authorization filter Middleware | 2 | Done | Auto check for user role and permissions better than add filter on all controllers actions
21 | Table paging and custom filter | 4 | Done | Custom table paging with backend to handle big data processing
22 | Hijri date | 2 | Pending | Add updated libraries and packages
23 | Upload - download files | 1 | Pending
24 | Pages code samples | 4 | Pending | Some common controlls and features
25 | Cyper security | 20 | Pending | Adding cyper security requrments on the code
26 | Change design colors to meet the identity | 14 | Pending
27 | Code cleaning | 12 | Pending
28 | Check all code performance and vulnerability |  | Pending
Total Days |  | 90